## Sheet1
Todays Date | 2020-05-13
ID | Status | Related Mission | Issue or basic action | Action details | Owner/s | Target Complete date | Date Completed | Further Notes
A1 | Completed | Itrative Development | Git up and running, matt to own but all to set up an account | All to get git up and running | Matt W | 2020-03-22 | 2020-03-22 | all to send user name to matt and matt to set up
A2 | Completed | Itrative Development | Set up discord, Chris S and Matt W have an accout already, Chris E to set up and link in | In meeting agreed to use discourd in we need to meet remotly, Chris E to set up an account as the rest of the team have an account. | Chris E | 2020-03-18 | 2020-03-16
A3 | Completed | Project Management | Send Mission roles to dan | Chris E to send agrred mission roles to Dan | Chris E | 2020-03-12 | 2020-03-12
A4 | Completed | Project Management | Finish Risk assesment | Chris E to finish risk assesment and all to send and risks to chris | Chris E | 2020-03-22 | 2020-03-22 | Extened a few days as all need to sign off,
A5 | Completed | Project Management | Complete code of conduct | Chris E to finish COC with input form team via whats app, to sign off in meeitng WC 16th March | Chris E | 2020-03-22 | 2020-03-22 | Extened a few days as all need to sign off,
A6 | Completed | Baseline implemention | Produce baseline | Chris E to set up a base line implmentation | Chris E | 2020-03-20 | 2020-03-19 | completed, all to review as a seprate action as meeting 20th march
A7 | Completed | Project Ideation | Chris S to start work on the Ideation | Chris S to complete project statemnt, in order for us to have a better understanding and document | Chris S | 2020-03-22 | 2020-03-28 | Ongoing team have an understanding of ideation chris S to uplod next few days
A8 | Completed | Project Ideation | Chris S to complete the project ideation | Chris S to Rewiew, problem statement, motavation, and project statemnt | Chris S | 2020-04-30 | 2020-05-13 | extended all have understaning but extended so chris S can develop documetation to good standard, extended (03/04/2020), extneded again while chris compleste and works on ir (10/04/2020), CLOSED INCOMPLETED
A9 | Completed | Project Management | Chris E to update COC as per meeting 3rd March | Update of COC needed to reflect us using discord and arranging the next meeting during each meeting | Chris E | 2020-03-15 | 2020-03-15 | COC updated to 2nd version all to review and sign off
A10 | Completed | Project Management | Chris E to update COC as per meeting 20th March | Update of COC needed to reflect us no longer meeing in the zone as default and change to remoting in | Chris E | 2020-03-21 | 2020-03-20
A11 | Completed | Project Management | Sign off COC and risk analysys | All to send any amendments to Chris E by 22nd at which point it will be signed off | All | 2020-03-22 | 2020-03-22
A12 | Completed | Itrative Development | set up doc to capture requirements for first run | Chris E to set up a doc and run meeting on 23rd March to capture requirements and prioritize (if time) (chris E to own but all to attend) | All | 2020-03-23 | 2020-03-23
A13 | Completed | Itrative Development | Matt to own git hub commits | Matt to own the git hub functionality | Matt W | 2020-04-30 | 2020-05-13 | THIS IS AN ONGOING ACTION TO BE CLOSED WHEN ASSINMENT IS COMPLETED, CLOSED INCOMPLETED
A14 | Completed | Itrative Development | Matt to commit the base line to github and set up the files | Matt to commit the base line to github and set up thre files (one for each team member) fo rus to edit and add out functions to | Matt W | 2020-03-29 | 2020-04-03 | Decided to only use one file (import file) for our function ratherthan one each)
A15 | Completed | Solution Design | Solution design | Matt W to complete his solutiuon design | Matt W | 2020-04-05 | 2020-04-05 | Matt has emailed lecturer for clarifacation on work done, and will tie in with chris s as missons are linked
A16 | Completed | Itrative Development | Assigned requirements | Matt W to work on requirements R2 , R6 | Matt W | 2020-04-05 | 2020-04-05
A17 | Completed | Itrative Development | Assigned requirements | Chris S to work on requirements R1 , R4 | Chris S | 2020-04-12 | 2020-04-17 | extended due to other commitments. Closed as resources issues but req coved in other development
A18 | Completed | Itrative Development | Assigned requirements | Chris E to work on requirements R14, R3 | Chris E | 2020-04-05 | 2020-04-05
A19 | Completed | Testing | Run testing | Mat to run testing on our completed requirements, possible mid week review of tesitng needed Matt to own | Matt W | 2020-04-14 | 2020-04-14
A20 | Completed | Project Management | document requirements for run 2 (CHECK DATES FORM MINUTES) | Chris E to document run 2 requirments based off our review | Chris E | 2020-04-27 | 2020-04-28
A21 | Completed | Project Management | amend gantt chate/add notes etc | Chris E to adust gant chart and add releven notes to re work as faling behind | Chris E | 2020-04-17 | 2020-04-22 | extended on the 17/04/2020
A22 | Completed | Itrative Development | Create relese on git hub to lock in version 1 | Matt W to create relese 1 To mark the end of the first run | Matt W | 2020-04-19 | 2020-04-19
A23 | Completed | Addional data | Addional data | Chris S to provide a CSV file to feed into our model. | Chris S | 2020-05-01 | 2020-05-13 | CLOSED INCOMPLETED
A24 | Completed | Testing | run testing and review for run 2 | Matt to run testing on our completed requirements for run 2 and produce a output doc with suggestions to take forward | Matt W | 2020-05-01 | 2020-05-01
A25 | Completed | Project Management | Find out what is need to "present" out work | Chris E to find out what we need to do to epresent this assinment as due to Covid the uni is effectivly closed, Chris E to email/speak to Mat Higgs | Chris E | 2020-05-01 | 2020-05-01 | Spoke to matt during our meeting
A26 | Completed | Project Management | Bullet point what we need to cover | Bullet point what we need to cover to prsent the assinment | Chris E | 2020-05-01 | 2020-05-02 | Completed
A27 | Completed | Itrative Development | package up the solution | Need to package up the solution either in a zip or relese on github | Matt W | 2020-05-08 | 2020-05-08
A28 | Completed | Itrative Development | Bring to gether assingment | Gather together all proof and docs and genarate a report all to do Chris E to lead and hand in by dead line | All | 2020-05-11 | 2020-05-13