## Timeline
[9 empty] | Run 1 |  |  | Run 2
EASTER BREAK
[5 empty] | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12
| Deadline date | owner | Notes on Actions | WC | 2019-02-23 | 2019-03-02 | 2019-03-09 | 2019-03-16 | 2019-03-23 | 2019-03-30 | 2019-04-06 | 2019-04-13 | 2019-04-20 | 2019-04-27 | 2019-05-04 | 2019-05-11
Gannt Ref |  |  |  | Actions
1 |  | Chirs E | A little later that dead line. 2nd and 3rd version created | Code of conduct
2 |  | Chirs E | produced a few days late. No impact to timeline | Risk reg
3 |  | Chirs E | Deliverd ontime | Baseline implemetation
4 |  | Chris S | Basic ideatiopn deliverd ontime.Chris "to take action (see log A | Project Ideation
5 |  | Matthew W |  | Solution design
6 |  | Chris S | Data not yet provided, We have went with a tact of putting some different data through our model at the end of the assinment | Additional data
7 |  | ALL |  | Review Baseline
8 |  | ALL |  | build run 1
9 |  | Matthew W | Fell a little behind (17/04/20). Disscussed going into run 2 and having a bisic run 2 to meet timeline (no need to adjust chart) | Review/test run 1
10 |  | All |  | build run 2
11 |  | Matthew W |  | Review/test run 2
12 |  | ALL |  | Contingancy/prep for presentation
13 |  | ALL |  | Present Solustion