## Risk
Risk | Risk Description | Impact Severity | Impact to Project | Probability | Risk Catogory | Owner | Action to be taken to mitagate or prevent | Action to be taken if risk arises
Illness | Team member is ill | Major | Possible missed deadline, or individual fall behind on individual mission as well as group mission. Possible for other team members to make up the missed work | Likely | MEDIUM | Chris E | Team members to update if ill ASAP and continue to communicate if possible | Gauge impact as soon as possible amend timelines if needed agree meeting remotely if needed
Under estimate task time | We under estimate how long a task will take to complete | Major | Possible impact so deadline and may push most of the assignment back | Maybe | MEDIUM | Chris E | Plan Gantt chat and agree time scale with all team members | Review timeline and actions ASAP, rearrange if needed.
Over reach team ability | We attempt a task that turns out to be outside of the team's or individuals ability | Major | This could impact deadlines and timetable is more education is needed. Re-work of idea or requirements as well as timetable might be needed also | Maybe | MEDIUM | Chris S | Review ideation as a team and agree on project | Review timeline and make changes to it as well as review scope of project or individual task. Possibility to speak to lecturer for help
Team member leaves | A team member leaves the team | Hazardous | This would impact the make up and plan of the project as well as deadline and mission assignments | Unlikely | MEDIUM | All | NONE - Out of our control | Re visit over all plan, possible need to re assign mission or speak to lecturer for guidance
Too many errors to fix in the time | We find a lot of errors and do not have time to fix or correct them (particularly if close to the assignment hand in date) | Major | Impact to deadlines may hold up dependant actions and tasks and delay them also | Likely | MEDIUM | All | Plan and review time line prior to project starting | Review time line. Prioritise error. Possible change scope to ignore errors or decide to proceed at risk with errors and document them
Inefficient skill or knowledge to complete a task | We or a team member attempts a task that is outside of their skill or knowledge (in the time required) | Minor | This could impact deadlines and timetable is more education is needed. Re work of idea or requirements as well as timetable might be needed also | Likely | MEDIUM | All | Agree project ideation and missions as a team | Review timeline and make changes to it as well as review scope of project or individual task. Possibility to speak to lecturer for help
Child care Issues | We all have young children and there is a chance we have childcare issues that prevent us form attending a meeting or doing work. | Minor | Possible missed deadline, or individual fall behind on individual mission as well as group mission. Possible for other team members to make up the missed work | Likely | MEDIUM | All | Plan and agree meeting times in advance to ensure this is mitagate as much as possible | arrange remote meeting if possible or feel it is productive. Review timeline and amend if needed
Technical issues | The team or an individual has some tech issues with software or hardware that causes an issue | Major | Could impact deadlines and possible hold up to parts of the assignment | Unlikely | MEDIUM | All | Frequent update within the team will help mitagate the impact of any issue | review timeline and amend in needed. Change scope of project if necessary
Data loss | The team or an individual has accidently loses data | Catastrophic | possible impact to deadlines as work might need to be re-done to make up for the data loss | Maybe | HIGH | All | Use of git hub as well as google drive to share work and files as well as individuals saving there on work locally should help mitagate the impact | review of action and timeline depending on the data loss and amount of re work required
Unable to access university due to coronavirus | We are unable to access university i.e. it is closed. | Hazardous | Depending on the details of the closure. Deadlines might be affected if we need support that we cannot access, meeting each other may not be possible or harder to arrange. This may impact deadlines and the timetable for the project. | Very unlikely | MEDIUM | All | NONE - Out of our control | review our meeting process and how we meet. This depends on whether it closes completely or just lectures and workshops etc.
Project too big | We over scope the project and give ourselves too much work | Hazardous | delayed deadlines as more time will need to be spent doing tasks. Re wok of project idea may be needed and will cause extra work and put the assignment behind as well | Maybe | MEDIUM | All | Project idea to be agreed by team as well as singed off by lecturer | Review time line and re arrange if needed. Look at the scope of the project as may need to reduce and re evaluate project
Member unable to attend meeting | Member or members unable to attend a meeting (or are extremely late) this could be transport issues or last minute child care issues) | Negligible | Missing meeting could result in more work for other remembers or at least more work to agree and re arrange the meeting | Almost certain | MEDIUM | All | Team to agree meeting dates in advance, this may differ week to week | Decide whether to go ahead with meeting or re arrange. Possibility you meet remote depending on circumstances. Look to assign task in the team members absence.
Too much work outside of this assingment | Other moduels and assingments creat a large worklosd for a time | Minor | possible missed dead;ines or meeting for some or all members | Maybe | MEDIUM | All | Agree plan and communicated with each other regularly and in meetings | Review time line and task/actions asap

## Risk Matrix
Risk severity
Risk Probability | Catastrophic | Hazardous | Major | Minor | Negligible
Almost certain | HIGH | HIGH | HIGH | MEDIUM | MEDIUM
Likely | HIGH | HIGH | MEDIUM | MEDIUM | MEDIUM
Maybe | HIGH | MEDIUM | MEDIUM | MEDIUM | LOW |  | Almost certain, Likely, Maybe, Unlikely, Very unlikely
Unlikely | MEDIUM | MEDIUM | MEDIUM | LOW | LOW |  | Catastrophic, Hazardous, Major, Minor, Negligible
Very unlikely | MEDIUM | MEDIUM | LOW | LOW | LOW
Probability | Definition |  |  |  |  | Severity | Definition
Almost certain | This is a risk we expect to happen at some point in this project |  |  |  |  | Catastrophic | This risk would potentally cause the project to hault or not be completed
Likely | There is a relistic chance this risk will happen |  |  |  |  | Hazardous | This risk would signifacatly impact the project and affect timescale and almost certainly cause deadlines to be missed without intervention
Maybe | There is a chance this risk will happen but it is not expected |  |  |  |  | Major | This risk would impact the project and potentally cause deadlins to be missed or the need to be changed or extended
Unlikely | There is no expectation that this risk will come to light |  |  |  |  | Minor | Minimum impact but may require intervention to ensure deadlines are not missed or extended
Very unlikely | There is almost no change of this risk happening |  |  |  |  | Negligible | There should be none or almost no impact of this risk arises